Software Estimation Model Shoot-Out:

SLIM-Estimate vs. PRICE-S

11/17/99

James T. Heires

Within the domain of software estimation tools, two popular models emerge: PRICE-S from Price Systems and SLIM-Estimate from Quantitative Software Management.  Here, the two models are investigated to determine their strengths and weaknesses.  A side-by-side analysis is then revealed.

# One problem -- Two models

The software estimation challenge has been with us for decades.  Department of Defense and commercial suppliers alike have struggled to understand the many intertwined relationships that drive cost, schedule and quality.  Is it size, functionality, team skill, process or the use of tools that drives the cost of software?

Both of the models reviewed here are parametric software estimation models.  Parametric models derive their value by requiring only an abstract description of the software to be developed and the development environment.  Inputs to parametric models include size, complexity, reuse, development process and team efficiency.

Size is an important input to these models and as such, special attention is paid to this parameter.  PRICE-S offers a commercial/military sizing utility for SLOC, while SLIM-Estimate offers a more flexible approach that allows combining and weighting to increase confidence.

Outputs from these models include cost, schedule and resources required to complete the project, and can be expressed in probabilistic terms.  Probabilistic outputs communicate the likelihood that certain estimated outcomes actually happen.

Both acquisition (development) and life cycle (maintenance) results can be estimated with each model.

# SLIM-Estimate: Software LIfecycle Management

SLIM-Estimate is a macro-level, dynamic, graphical estimating model.  Part of a family of quantitative software management products including SLIM-Control and SLIM-Metrics.  SLIM-Estimate is based upon empirical data analysis work published by Larry Putnam1.

Inputs to the model are organized in a logical, flexible format.  Sizing can be entered using abstract terms or broken down into functions or modules2.

The outputs from SLIM-Estimate are many and varied.  A graphical staffing profile is based on an empirically derived Rayleigh curve3.  This output is unique in that it is interactive.  Once an initial solution has been derived, the user can study "what-if" scenarios such as:

- What if the customer wants additional functionality?

- What if we experience unplanned staff turnover?

- What if we spend more time in requirements capture?

This interactive nature of SLIM-Estimate allows for powerful size/time/effort/quality trades early in project planning.

Fifty proprietary department of defense projects form the basis of the software equation upon which this model is based.  This equation has since been calibrated with over 4500 projects from many application domains.  The Putnam software cost equation is:

Effort = B * Size3 / (PP * T4)

Where:

Size = Lines of Code or function points to be developed

B = Skills factor that depends upon size

PP = Productivity Parameter from empirical data

T = Schedule (time)

Visible shivers running down my spine4

One can readily notice by the exponents in the above formula that a severe effort penalty is given to increasing the size or shortening the schedule.

Another powerful SLIM-Estimate feature is the ability to visually compare historical data to the current estimate5.  Showing actual performance from similar projects next to the current estimate and industry trends provides much needed justification.

# PRICE-S

If you need a second opinion as you seem to do these days6

PRICE-S is a parametric software estimation model originally developed at RCA in the late 1970's.  One of a family of cost estimation tools including PRICE-H (hardware) and PRICE-M (electronic components).

PRICE-S is a process-oriented model that was validated with empirical data.  This model has separate sizing modes for commercial and military software applications.  Acquisition and lifecycle estimates are carried out as independent activities, but with data dependencies.

The PRICE-S software cost equation is:

Effort = (ePROFAC * [VOL f (PROFAC)]) / 10007

Where:

PROFAC = Productivity factor from empirical data

VOL = Software volume (a function of size)

The input format consists of an estimating breakdown structure to assist decomposing a large system into its component parts8.  Users familiar with PRICE-H will be right at home with the PRICE-S interface.  Reused code is characterized as either purchased or furnished, while developed code is characterized separately.

The primary PRICE-S output is a tabular report format.  However, several graphs are also available9.  In addition, the probabilistic report format can be shown as either a frequency distribution or a probability distribution.  This report can also be exported to an ASCII text file for importing to other tools.

# Side-by-Side comparison

It's the stupid details that my heart is aching for6

|  | SLIM-Estimate | PRICE-S |
| --- | --- | --- |
|  | Published model | Proprietary model |
| Performance | Interactive and fast | Good, but Monte Carlo is slow |
| Stronger for | IT domain | Real-time domain |
|  | Simple economic model | Detailed economic model |
| User Interface | Graphical, interactive | Graphical, batch feel |
|  | Easy to use, intuitive | Terminology, interface requires training |
| Inputs |  |  |
| Size* | SLOC | SLOC |
|  | Function Points | Function Points |
|  | N/A | Predictive Object Points |
|  | 17 other size units, multiple methods | N/A |
|  | New-never designed code | New-never designed code |
|  | N/A | New-already designed code |
|  | Modified code | Modified code |
|  | Reused code | Reused code |
| Domain* | Application type (9 predefined) | Platform (12 predefined) |
| Development process | Waterfall assumed** | 5 choices available |
| Project Goals | Schedule (overall) | Schedule (by phase) |
|  | Effort | N/A |
|  | Cost | N/A |
|  | Staffing | N/A |
|  | Reliability | N/A |
| Productivity | Tools/methods | Tools |
|  | Technical difficulty (14 factors) | Technical difficulty (6 factors) |
|  | Personnel (9 factors) | Personnel (6 factors) |
|  | Reuse environment | N/A |
|  | Productivity (PI)** | Productivity by CSC/CSCI (PROFAC)** |
| Outputs |  |  |
| Size | Computed from sizing utility | Computed from sizing utility |
| Effort | By phase (4)** | By phase (10)** |
|  | By skill (9) | By skill (7)** |
|  | N/A | By element (CSC, CSCI) |
|  | Integration included in total effort | Integration separate from development |
| Cost | Converted from effort using average rate | Converted from effort using rate by skill |
|  | Escalates using single inflation rate | Escalates using yearly inflation rates and cost of money, other factors |
| Schedule | Optimum schedule offered - can be traded off for effort/size interactively. | Optimum schedule offered - can be constrained only (penalty) |
| Reports | 150 reports/graphs | 42 reports/graphs |
|  | Export to MS Project | Export to MS Project and ACEIT |
| Staffing | People by month by phase | Must be derived from effort |
| Field Reliability | Derived from Rayleigh distribution** | N/A |
| Risk Assessment | Related to project goals (probability of success) | Calculates range of numbers, but does not relate to goals |
|  | Normal distribution of inputs | 4 distribution choices available |
| Probability | Default mode | Deliberate action needed |
| Comparisons | Historical data and industry trends shown next to estimate | Calibration done before modeling but not compared to estimate |
| Training | 1.5 days | 5 days |
|  | Over 100 employees trained | Less than 10 employees trained |
| Historical data | 120 projects from GS, ATS | Opportunistic only - no database |

* Required inputs

** Calibration recommended

You can look in my eyes and you can count the ways6

# Conclusions10

Both models reviewed here are strong commercially successful parametric cost estimating tools.  SLIM-Estimate has a distinct advantage in its ease of use, where the PRICE-S advantage is its ability to be calibrated to a detailed level.  In addition, the availability of historical data allows SLIM-Estimate to be calibrated much more quickly than PRICE-S.  PRICE-S is being mandated for use on some DoD contracts.

I suggest we maintain the use of both tools, but favor SLIM-Estimate for times when we have a choice or have suitable historical data available.  We should use PRICE-S for those situations where customers demand its use and for times when detailed calibration is needed.

I don't know how much more of this I can take.4

# About the author

James T. Heires is a fourteen-year veteran of the software industry, the majority with Rockwell Collins, Inc.  His professional experiences include design of electronic flight instrumentation, flight management systems, and consumer electronics.  Additionally, Mr. Heires' work in software process improvement culminated with the achievement of SEI CMM Level III in two Rockwell Collins business units.  Most recently, James is improving the state-of-the-practice in project cost estimating using parametric modeling techniques.

James has been formally trained to use SLIM-Estimate, but not PRICE-S.  Although every effort was taken to present an accurate, balanced review, some PRICE-S information presented here may inadvertently be incomplete or incorrect.

R

c

# Text boxes

7 PRICE-S Software Development and Support Cost Model User Guide, PRICE Systems, Mt. Laurel, NJ, 1997.

5 Similar-to comparison

1 A General Empirical Solution to the Macro Software Sizing and Estimating Problem, Lawrence H. Putnam, IEEE Transactions on Software Engineering, July 1978, Vol. SE-4, No 4, pp. 345-361.

4 Watching the Detectives, Elvis Costello and the Attractions, produced by Nick Lowe, from the album My Aim is True (rc 0271), Rykodisc, 1977.

8 PRICE-S Estimating Structure

2SLIM-Estimate sizing

9 PRICE-S Staffing Profile

3 SLIM-Estimate Staffing Profile

10 Introduction to Software Estimation Techniques and Tools, Software Productivity Consortium, SPC-97001-MC, version 01.02.00, June 1997.

6 I want you, Elvis Costello and the Attractions, produced by Nick Lowe, from the album Blood and Chocolate (rcd 20282), Rykodisc, 1986.