## ISSUES
SEQ# | ISSUE NAME | ORGINATOR | SUBMIT DATE | AREA | MODULE NAME | DESCRIPTION | PRIORITY | STATUS | BUSINESS IMPACT | EXPECTED RESOLUTION DATE | ASSIGNED TO | SUGGESTED SOLUTION | PROGRESS | COMMENTS
1 | User cannot print KITR001 | Mike | 2005-02-04 | Accounting | KITN001 | From screen KITN001 user cannot print the account (KITR001) report; all other reports are printable | High | In Progress | Training and implementation will need to be put on hold | 2005-02-11 | Jeff | Most likely KITR001 is producing some special characters but not sure | 02/15/2005: Ann has assigned to Jeff 02/16/2005: Jeff is working with Ann in the accounting area
2 | SSN Field missing from Payroll interface | Ann | 2005-03-01 | Accounting | Interface | Since 2/28, SSN field does not cross | High | Open | Cannot do parallel testing | 2005-03-28
3 | Scanner not available | Avi | 2005-03-03 | Development |  | Symbol scanner has not arrived yet; cannot do the unit testing | Medium | Open
4 | Field alignments | Avi | 2005-03-03 | Development | KITN005 | Purchase date, ordered date and the remaining fields underneath them are mis-aligned. This makes them hard to read | Low | Open