Handling Uncertainty In Project Planning

By Dmitri Ilkaev

Introduction

Majority of project planning efforts today are still performed in the strictly “deterministic” manner where all project tasks are assigned with well defined timeframes to execute and resources to implement. At the same time we all know that real life necessitates corrective actions: resources are not always available, extra tasks pop up during the course of the projects and what happens most frequently is the initial estimate of the time required to perform a certain task is no longer valid. It’s easy to mentally grasp such uncertainties and have accurate estimate when dealing with a few variables, however with large scale projects having multiple uncertainty factors of a different nature and character such analysis can not be performed manually and demands that very special efforts are required for the accurate project assessment. Such uncertainty in the project planning is widely recognized in a lot of industries and a wide variety of different tools exists to help to optimize the planning process and minimize the associated risks.  These tools cover a wide range of offerings from the mathematically rigorous and sophisticated solvers (mainly constraint based programming) to different Excel adds on (VBA macro based) doing similar things but on a simpler level (you could find even a freebie doing some optimization of your Excel based projects or dependencies).

Approach

In this paper we share the approach which we recommend to implement when dealing with the large and cumbersome projects, their planning, assessment and optimization. We have been focusing on the software development projects, however this approach is valid for the wider selection of projects in industries.

Our situation is very common for a product development organization: How to rapidly develop an accurate project plan estimate which is critical to the overall development lifecycle (resources, relation to other projects and dependencies on other deliverables should be always well defined) and at the same time minimize the time spent performing “if-then-else” analysis (our business and technical analysts and project managers have their hands full doing “real things” – implementing new customer requested functions and working on the next release of the product).

By setting up a few extra steps in our planning processes and applying a specialized tool against our project plan, we believe that we’ve found the right solution and were able to define the correct approach to this problem.

Our process of planning and assessment consists of the 5 main steps:

- Define the project

During this phase we are putting together the regular project plan in a MS Project with the main tasks, timeframes and deliverables. Project Plan can be created either manually or be generated as the result of other efforts (doing some preliminary use cases or object design or working with the cost estimate tools).

- Identify uncertainly

In this phase we need to determine which tasks or their inputs in the plan are uncertain, what we know about these uncertainties and what would be the best way to describe these uncertainties, their behavior and known range of values they might cover. During this phase we also need to identify what are the most critical results or outputs of our plan we want to look at, analyze and optimize.

- Apply the tool and implement the model

We’ve selected Palisade’s @Risk for Project (http://www.palisade.com) as our project optimization tool from the wide variety of the other available packages. We believe that this tool is a good match to our requirements: be integrated with the MS project, easy to set up model, sufficient depth of simulation and outputs, ease of analysis. A particular tool selection only affects the way how uncertainly model will be applied, the general approach to the problem handling will remain the same.

- Run simulation

As the result of the Monte Carlo simulation (parameters of this simulation can be configured as well) we obtain the ranges and probabilities of all outcomes for the outputs that we’ve identified during model setup (normally it’s the ranges of the duration of the particular phases or the project with the most critical dependencies, overall project timeframe, etc.)

- Make a decision

Based on the simulation results and looking at the outputs of the model, we obtain the information about most critical characteristics of the project. This data serve as the basis for the following optimization and corrective actions.

Working with the tool

@Risk is tightly integrated with MS Project and looks as the additional tool set on the MS project panel (see picture below). By selecting particular project parameters (for example duration of the task) and clicking on the “Define Distribution” icon on the @Risk tool bar, we can set up model characteristics.

Figure 1. Model Setup

The tool is quite flexible in definition of the distribution widows: out of the box it’s easy to find anything from the uniform or normal distribution up to the more exotic ones, see picture below.

Figure 2. Different available distribution functions

We use our past projects experience and “historical” knowledge to define the possible ranges for a different tasks and distribution functions. For any distribution function we can define its “fine structure”, like average value, standard deviation, etc. There is also another advanced feature which allows to add additional “custom” uncertainties to the selected tasks or group of tasks.

Model outputs are specified in the same manner: click on the selected cell (for example, finish date or duration) and specify it as the output. You can see the corresponding notations in the @Risk:Functions column of the Project, see picture below.

Figure 3. Specifying model outputs

An implemented model could be enhanced by putting additional conditions (see on the previous picture a @Risk icon with an “IF” on it, 6th from the left on the tool bar). For example, we know that if we’d spent all available time on doing one particular task another dependent task should happen only within strictly limited timeframe and that’s exactly what “If-Then” function of the model is supposed to take into account.

Figure 4. Model enhancement with “If/Then” conditions

After running the simulation, the output window will look like as presented below.

Figure 5. Simulation results

You can see the defined outputs of the finish dates for the elaboration and construction phases as well as the total duration of the construction phase (as they were defined as the outputs of the model). Results show quite a significant range in the finish date for the construction phase (overall more than a month uncertainty in the final date) and we might want to reevaluate the project setup (sequence and task dependencies as well as resource allocation). The simulation data provide the answers on the additional questions, for example to give the probability that the project or its phase will be finished before the certain date together with providing more granular information about project dynamics and showing the most critical parameters for the project cycle (sensitivity analysis)

Figure 6. Scenario and Sensitivity Analysis

There are multiple ways of the graphical representation of the simulation results which also makes an analysis tasks easier, see picture below.

Figure 7. Graphical representation of results

Since we mentioned an Excel based enhancements, its worth saying a few words about them (Palisade also has another version working for Excel). For these set of add ins, we would import our project plan into Excel spreadsheet and then the similar logic of a setting up a model with the risks and uncertainties and following simulation should take place. We’d tried What’s Best from Lindo Systems, OptiRisk from OptiGroup and they work in a similar fashion, although recognized leaders like Solver or Crystal Ball add more functionality and better user interface.

As we discussed above, the general approach will stay the same regardless of the tool being used. There are two other tools imilar to @Risk: Risk + from http://www.cs-solutions.com and Pertmaster from http://www.pertmaster.com/.

For due diligence we did set up of the same model in the Pertmaster, see below:

Figure 8. Model setup in PERTMASTER

Simulation shows very similar results. Graphical output from this tool is slightly different and just for the sake of illustration we’ve selected different model output and criteria to show. On the picture below you can see the projected finish date of the project and associated probability of this event.

Figure 9. Results graphical representation in Pertmaster

Conclusion

In this paper we have described the approach on how to handle uncertainties in project planning. This approach includes development and implementation of the risk model which describes these uncertainties followed by running a simulation to generate predefined project outcomes or the most critical parameters. We also touched briefly on several available tools and provided some examples on how they function (mostly @Risk from Palisade and Pertmaster).