## Summary
Effort Planning | Amount | Effort (h) | Varianten & Cycles
Test Point Analysis (Creation) | 8.3333 | 6.25
Test Point Analysis (Execution) | 8.3333 | 4.1667 | 12.5
Totals |  |  | 18.75 | manhours

## Details
ID | Workstream | Business Process | Use Case | [13 empty] | Creation |  |  |  |  | Execution |  |  |  |  | Systems
Business Processes |  |  | Business Component/Use Case | Planned Release | Manual/System | Level | Relevant for launch | To be Tested | Current Development Status | Current Test Status | System Design available | System Requirements available | Use Case/Usage Scenario available | Testcase available | Variances | Number of Steps in Testcase | Interfaces with other Testcases | Establishing a Baseline Result | Complexity Weight | Complexity | Classicication | Preconditions | Verifications | Complexity Weight | Complexity base Scenario | Classicication | System 1 | System 2 | System 3 | System 4 | System x
EXAMPLE 1 | [5 empty] | P | Y | P | [6 empty] | 1 | 2 | 1 | 0 | 3 | 6 | Simple | 0 | 0 | 2 | 6 | Simple
EXAMPLE 2 | [5 empty] | S | Y | S | [6 empty] | 1 | 3 | 0 | 0 | 3 | 6 | Simple | 0 | 1 | 4 | 6 | Simple
EXAMPLE 3 | [5 empty] | C | Y | C | [6 empty] | 2 | 4 | 1 | 0 | 10 | 6 | Simple | 0 | 2 | 12 | 8 | Average
EXAMPLE 4 | [5 empty] | P | N | ... | [6 empty] | 3 | 5 | 0 | 0 | 15 | 8 | Average | 0 | 3 | 24 | 12 | Complex
EXAMPLE 5 | [5 empty] | S | N | ... | [6 empty] | 3 | 6 | 1 | 0 | 21 | 12 | Complex | 0 | 4 | 30 | 12 | Complex
EXAMPLE 6 | [5 empty] | C | N | ... | [6 empty] | 3 | 7 | 0 | 0 | 21 | 12 | Complex | 0 | 5 | 36 | 12 | Complex
Note on G2: Hutchison: P - Process S - Subprocess C - Component/Use Case
Note on I2: Hutchison: P - Business Process S - Test Scenario C - Test Case
Note on J2: Hutchison: A - Analysis D - Development T - Test
Note on K2: Hutchison: P - Preparaion T - Test R - Ready for Acceptance H - Handover to Operations